## All stories and tasks
Phase 1 — Initiation and Discovery
CRMNI-01 — Project governance and scope baseline
User story: As a project sponsor, I want scope, governance, success criteria, and delivery cadence defined so the implementation is controlled from day one.
Tasks
Run project kickoff with business and IT stakeholders
Define in-scope and out-of-scope modules for phase 1
Define project objectives, KPIs, and success measures
Build stakeholder register and RACI
Define sprint cadence, status reporting, and governance meetings
Create RAID log and change control process
CRMNI-02 — Current-state CRM and process assessment
User story: As a solution team, we need to understand the current CRM, sales process, and pain points so the new system solves the right problems.
Tasks
Inventory current entities/tables, forms, views, dashboards, flows, plugins, and JS
Document current inside sales and outside sales processes
Document current lead, opportunity, case, and contact management process
Capture current reporting and manual workarounds
Identify duplicate data pain points and usability issues
Document legacy customizations that should not be carried forward
CRMNI-03 — Data source and integration assessment
User story: As an integration architect, I want all current source systems and interfaces documented so the new CRM integration model is complete.
Tasks
Identify all source systems feeding the current CRM
Document current Boomi integrations and data flows
Inventory Data Warehouse source objects and refresh frequency
Inventory Dotdigital touchpoints and synchronized data
Inventory Finance & Operations invoice data needed in CRM
Document inbound, outbound, and reporting dependencies
CRMNI-04 — Reporting and KPI requirement discovery
User story: As a sales leader, I want reporting requirements documented so dashboards and analytics are built correctly in the new CRM.
Tasks
Identify KPIs for reps, territory managers, directors, and executives
Define required sales dashboards and operational reports
Identify territory, pipeline, product, and case reporting needs
Capture invoice visibility and customer financial summary needs
Capture campaign and engagement reporting from Dotdigital
Identify reports that can be retired
CRMNI-05 — Migration scope and archival strategy
User story: As a business owner, I want migration scope defined so only the right data moves into the new CRM.
Tasks
Define which records are active and must migrate
Define optional historical data to migrate
Define archive-only data
Define document/attachment migration scope
Define data retention and legal/compliance constraints
Produce migration scope sign-off
Phase 2 — Solution Design
CRMNI-06 — Target solution architecture
User story: As a solution architect, I want a target-state architecture defined so CRM, integrations, and reporting align to one design.
Tasks
Design overall application architecture
Define source-of-truth by domain
Define Dataverse vs external system ownership
Define integration patterns for DW, Dotdigital, and F&O
Define non-functional requirements: performance, audit, supportability
Produce architecture diagram and review with stakeholders
CRMNI-07 — Target data model design
User story: As a CRM architect, I want the target data model designed so the new system supports the business cleanly without legacy baggage.
Tasks
Design Account model
Design Contact model
Design Customer Location / Site model
Design Territory and Territory Location model
Design Coverage Assignment / ownership model
Design Product, Lead, Opportunity, Case, and Invoice summary structures
Define relationships, external IDs, required fields, and naming standards
CRMNI-08 — Territory and ownership model design
User story: As a sales operations lead, I want territory and ownership rules defined so client coverage works across Australia and New Zealand.
Tasks
Define country, region, and territory hierarchy
Define inside sales vs outside sales coverage rules
Define named-account override rules
Define location-level vs parent-account ownership rules
Define reassignment rules and escalation paths
Define territory manager and director rollups
CRMNI-09 — Security and access model design
User story: As a system administrator, I want a security model defined so users only see and edit what they should.
Tasks
Define business units, teams, and role approach
Define security roles for reps, managers, directors, admins, marketing, finance view-only
Define hierarchy security needs
Define field-level security needs
Define sharing rules for overlay/dual coverage scenarios
Define environment and admin access model
CRMNI-10 — UX, app navigation, and UI design
User story: As a sales user, I want a clean and role-based CRM experience so I can work faster with less friction.
Tasks
Define persona-based app experiences
Design sitemap/navigation for inside sales, outside sales, and leadership
Create wireframes for Account 360, Lead workspace, Opportunity workspace, and dashboards
Identify pages needing custom UI using HTML/CSS/JavaScript or custom pages
Define form simplification and section layout standards
Review UX designs with business users
CRMNI-11 — Integration architecture design
User story: As an integration architect, I want the direct Data Warehouse integration model defined so the new CRM no longer depends on Boomi.
Tasks
Define integration flow from Data Warehouse to Dataverse
Define staging, validation, and upsert strategy
Define alternate keys/external IDs
Define sync schedules and retry behavior
Define reconciliation and exception handling
Define Boomi decommission plan
CRMNI-12 — Data quality, deduplication, and migration design
User story: As a data lead, I want data cleansing and migration rules defined so the new CRM starts with trusted data.
Tasks
Define deduplication rules by object
Define match keys and survivorship rules
Define cleansing rules for addresses, emails, phone numbers, territory mapping
Define data transformation rules from source to target
Define trial migration cycles and reconciliation checkpoints
Produce migration mapping workbook
Phase 3 — Platform Foundation
CRMNI-13 — Environments, solution structure, and ALM setup
User story: As a platform team, we want environments and solution structure set up so development and deployment are controlled.
Tasks
Provision DEV, TEST, UAT, and PROD environments
Create base managed/unmanaged solution structure
Configure publishers, prefixes, and environment variables
Configure service accounts and connection references
Define branching and deployment process
Set up deployment checklist and release documentation
CRMNI-14 — Base platform and reference data configuration
User story: As a system admin, I want base configuration completed so feature build can start on a stable foundation.
Tasks
Configure currencies, business settings, fiscal periods, and regional settings
Load choice values and reference data
Configure email, auditing, duplicate detection, and search settings
Configure app modules and base navigation shells
Configure users, teams, and test accounts
Validate baseline environment readiness
Phase 4 — Core CRM Build
CRMNI-15 — Customer master: Accounts, Contacts, and Locations
User story: As a sales rep, I want a complete customer master model so I can manage organizations, people, and sites accurately.
Tasks
Build Account table fields and relationships
Build Contact table extensions and relationships
Build Customer Location / Site table
Configure forms, views, quick views, and subgrids
Add validation and business rules
Build parent-child and location relationships
Unit test create/edit/search scenarios
CRMNI-16 — Lead management
User story: As an inside sales rep, I want lead capture, qualification, routing, and conversion processes so leads move efficiently through the funnel.
Tasks
Configure Lead fields and forms
Define lead source and scoring fields
Build qualification statuses and required stage rules
Configure lead-to-account/contact/opportunity conversion behavior
Build lead routing logic
Create lead views and work queues
Test qualification and conversion scenarios
CRMNI-17 — Opportunity management
User story: As a sales rep, I want an opportunity process aligned to Metagenes’ sales cycle so I can manage pipeline accurately.
Tasks
Configure Opportunity stages and business process flow
Add required fields by stage
Configure revenue, estimated close date, and forecasting fields
Build opportunity ownership and collaborator model
Configure close-as-won/close-as-lost reasons
Build opportunity views, dashboards, and notifications
Test opportunity progression and close scenarios
CRMNI-18 — Product catalog and pricing
User story: As a sales user, I want products and pricing available in CRM so I can work opportunities with the correct commercial data.
Tasks
Configure product families, products, units, and price lists
Define active/inactive product behavior
Map product categories and segmentation
Configure opportunity product behavior
Define pricing source and refresh approach from DW/F&O if applicable
Create product views and admin maintenance screens
Test quoting/product selection scenarios
CRMNI-19 — Case management foundation
User story: As a sales and service user, I want case visibility and management in CRM so customer issues are visible and actionable.
Tasks
Confirm case scope for phase 1
Configure Case fields, forms, and views
Define case statuses and priorities
Relate cases to accounts, contacts, and opportunities
Build case queues/views for business users
Add summary visibility on Account 360
Test case create/update/close flows
CRMNI-20 — Territory assignment and routing automation
User story: As sales operations, I want customer and lead assignment automated so records go to the right territory and owner.
Tasks
Build Territory and Territory Location tables
Build coverage assignment table(s)
Build lead assignment logic
Build account/site ownership assignment logic
Build reassignment and override logic
Log routing decisions for auditability
Test territory edge cases and exceptions
CRMNI-21 — Activities, tasks, alerts, and work management
User story: As a sales rep, I want my tasks, calls, appointments, and follow-ups organized so I can execute efficiently.
Tasks
Configure activity forms and views
Build activity timeline improvements where needed
Create task and follow-up views by role
Build alerts/reminders for stale leads and opportunities
Configure dashboards for daily workload
Validate activity rollups on account/contact/opportunity
Test timeline and notification behavior
CRMNI-22 — Dashboards, custom pages, and embedded HTML/CSS/JavaScript
User story: As a user, I want a modern CRM experience so key information is easier to consume and act on.
Tasks
Build role-based model-driven apps
Build Account 360 page
Build Lead workspace page
Build Opportunity workspace page
Build manager dashboard and executive dashboard
Develop approved HTML/CSS/JavaScript web resources or custom pages
Test security trimming, responsiveness, and load performance
Phase 5 — Integrations
CRMNI-23 — Data Warehouse integration framework and Boomi replacement
User story: As an integration team, we want a direct DW-to-CRM framework so the new system no longer depends on Boomi.
Tasks
Build integration entry pattern and staging model
Build reusable integration logging framework
Define and implement upsert pattern using alternate keys
Build error handling and retry process
Create interface control documentation
Execute side-by-side validation against current outputs
Plan and execute Boomi switch-off
CRMNI-24 — DW master data synchronization
User story: As a business user, I want customer and reference data synchronized from the DW so CRM stays current.
Tasks
Build Accounts sync
Build Contacts sync
Build Customer Locations sync
Build Products sync
Build Territory/geo mapping sync
Build owner assignment support fields from source data
Reconcile loaded data against source extracts
CRMNI-25 — Dotdigital integration
User story: As a marketing and sales user, I want Dotdigital integrated so engagement and consent data are aligned with CRM.
Tasks
Define field mapping for contacts/leads/accounts
Define consent, subscription, and suppression rules
Define segment/export logic
Build or configure campaign response/engagement sync
Surface engagement summary on CRM records
Build integration monitoring and exception handling
Validate end-to-end sync with marketing team
CRMNI-26 — Finance & Operations invoice visibility
User story: As a sales user, I want invoice visibility from F&O so I can understand customer financial context without leaving CRM.
Tasks
Define invoice data required in CRM
Design invoice summary/read-only data model
Build sync or data exposure process
Surface invoice history and aging on Account 360
Build finance read-only views and dashboards
Validate reconciliation with F&O team
Test security access to finance data
CRMNI-27 — Integration monitoring and reconciliation
User story: As a support team, we want monitoring and reconciliation in place so integration issues are detected quickly.
Tasks
Build integration run log tables/views
Build failed-record/error queue handling
Build reconciliation reports by object
Build alerting for missed or failed loads
Define daily and weekly support procedures
Create runbooks for common failures
Phase 6 — Data Quality and Migration
CRMNI-28 — Data profiling, deduplication, and cleansing
User story: As a data migration team, we want source data profiled and cleaned so only trusted data is loaded to the new CRM.
Tasks
Profile Accounts, Contacts, Leads, Opportunities, Cases, Products, and Locations
Identify duplicate patterns and orphan records
Clean invalid addresses, emails, phones, and reference values
Resolve ownership and territory mapping issues
Execute dedupe rules and survivorship decisions
Produce clean migration extracts
CRMNI-29 — Trial migration cycles
User story: As a project team, we want trial migration cycles completed so final migration is predictable.
Tasks
Load sample migration data to DEV/TEST
Validate field mappings and relationships
Validate converted users/owners/teams
Validate data volumes and performance
Run business validation workshops on migrated data
Fix mapping issues and repeat as needed
CRMNI-30 — Final migration preparation and production load
User story: As a cutover team, we want final migration scripts and production load procedures ready so go-live is controlled.
Tasks
Finalize production migration runbook
Finalize cutover extracts and transformation scripts
Freeze source data rules for cutover window
Prepare rollback/contingency plan
Load production data during cutover
Execute post-load validation and sign-off
Phase 7 — Testing, Training, and Readiness
CRMNI-31 — System integration testing and user acceptance testing
User story: As a business owner, I want the solution fully tested so the new CRM is ready for production use.
Tasks
Create SIT test scripts by process area
Execute SIT across CRM, DW, Dotdigital, and F&O touchpoints
Create UAT scripts and expected outcomes
Run UAT with business users
Log and triage defects
Retest fixes and obtain sign-off
CRMNI-32 — Security, performance, and regression validation
User story: As a platform owner, I want non-functional validation completed so the system is secure and reliable.
Tasks
Execute security role and hierarchy access testing
Validate field-level and record-level permissions
Execute performance tests for forms, views, dashboards, and integrations
Execute regression test pack after major releases
Validate audit logging and monitoring coverage
Sign off on non-functional readiness
CRMNI-33 — Training and change management
User story: As an end user, I want training and support materials so I can adopt the new CRM confidently.
Tasks
Create role-based training plan
Create training guides and quick reference sheets
Create admin support guide
Train super users/champions
Run end-user training sessions
Capture feedback and refine materials
CRMNI-34 — Cutover planning and go-live readiness
User story: As a project team, we want a complete cutover plan so go-live happens in a controlled manner.
Tasks
Create detailed cutover checklist
Define go/no-go criteria
Define freeze window and communications
Confirm production support coverage and escalation matrix
Confirm final deployment package and migration readiness
Hold cutover rehearsal and readiness review
Phase 8 — Go-Live and Hypercare
CRMNI-35 — Production deployment and go-live
User story: As a project sponsor, I want the new CRM deployed successfully so the business can transition to the new platform.
Tasks
Deploy production solution components
Execute production data migration
Enable integrations and scheduled jobs
Execute smoke testing
Validate critical reports, dashboards, and record access
Obtain go-live approval and announce launch
CRMNI-36 — Hypercare and support transition
User story: As a support organization, we want hypercare completed and ownership transitioned so the system remains stable after launch.
Tasks
Stand up hypercare team and support channel
Monitor production issues and prioritize fixes
Reconcile integration and data issues daily
Track adoption metrics and user feedback
Transition support to steady-state operations
Conduct lessons learned and closeout review
Recommended Jira add-ons under the Epic
In addition to the stories above, create these issue types as needed:
Spikes
Use Spikes for:
current-state assessment
target architecture
integration architecture
migration design
territory design
Bugs
Create bugs during:
SIT
UAT
hypercare
Risks / impediments
Track separately in Jira or your RAID log:
Data Warehouse source quality
territory ownership conflicts
Dotdigital consent mapping issues
invoice reconciliation gaps with F&O
delayed business sign-offs
source data readiness
Suggested labels/components in Jira
Use labels or components like:
Discovery
Architecture
DataModel
Security
UIUX
CoreCRM
Territory
Integration-DW
Integration-Dotdigital
Integration-FO
Migration
Testing
Training
Cutover
Hypercare
Practical issue count
This backlog will likely become roughly:
36 Stories/Spikes
140 to 180 Tasks/Sub-tasks
20+ Bugs during testing and go-live
Best way to enter this in Jira
Create these in this order:
1. Phase 1 stories
2. Phase 2 design stories
3. Foundation setup
4. Core build
5. Integrations
6. Migration
7. Testing and training
8. Go-live and hypercare
That sequence will make dependencies much easier to manage.
Say convert this into a Jira CSV format and I’ll structure it with columns like:
Issue Type, Summary, Epic Link, Parent, Description, Labels, Priority.