Sales CRM Account Deduplication Document

Paul Aneng 4-13-2026. Metagenics

## 1. Purpose & Scope

This document defines the end-to-end execution operating model for deduplicating Account records in CRM. It establishes the execution approach, responsibilities, and governance controls required to safely identify, validate, execute, and, if necessary, roll back Account deduplication activities.

The scope of this document includes:

- Accounts (Practitioner, Retail)

- SQL-based preview and validation

- Execution in UAT and Production

- Record reassociation of activities, and other account related records

- Production rollback via Dynamics 365 environment restores

This document applies to all personnel involved in Account data management, including CRM, Sales Operations, Finance, IT, and Data Stewardship functions.

## 2. Execution Principles

The following principles govern all deduplication activity:

- Deduplication is a business-controlled process, not technical cleanup

- Practitioner, Retail, and Sample accounts are not interchangeable

- SQL previews must precede any execution

- All execution must be validated in UAT before Production

- CRM account merge is irreversible

- Record reassignment during merge is a material business impact

- Production rollback is performed via environment restore, not record-level correction

- Accountability increases as execution risk increases

## 3. Execution Methodology

Deduplication is executed using a three-stage-controlled approach:

- SQL Previews – Analysis and validation only (no data changes)

- Execution in UAT – Behavioral and reassignment validation

- Execution in Production – Controlled, auditable change

No stage may proceed without approval from the accountable role for the prior stage.

## 4. Execution Plan & RACI

### Roles (Summary)

- Exec Sponsor – Executive accountability and escalation authority

- CRM Product Owner – Overall accountability for CRM outcomes

- CRM Admin – Dynamics 365 configuration and execution

- Data Steward – Data correctness and merge approval

- Sales Ops – Territory, ownership, and reporting validation

- Finance Ops – Financial integrity and ERP considerations

- IT / Integration Lead – System stability and integrations

### Execution Plan & RACI Table

| Phase | Phase Description | Task Description | Responsible | Accountable | Consulted | Informed | Timeline |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 –Governance & Readiness | Establish ownership and controls | Appoint Exec Sponsor, CRM Product Owner, Data Stewards, escalation paths | Exec Sponsor | CRM Product Owner | Sales Ops, Finance Ops, IT | CRM Users | W1 |
| 1.1 |  | Review and formally approve Deduplication Group Rules | CRM Product Owner | Exec Sponsor | Data Steward, Sales Ops, Finance Ops | CRM Admin |  |
| 1.2 |  | Restrict merge permissions to approved roles | CRM Admin | CRM Product Owner | IT Security | CRM Users |  |
| Phase 2 – SQL Previews & Validation | Identify and validate duplicates without data change | Partition Accounts by Type, Country, and Purpose | CRM Admin | CRM Product Owner | Data Steward | Sales Ops | W2- W 4 |
| 2.1 |  | Run SQL previews to identify duplicates and proposed survivors | Data Steward | CRM Product Owner | Sales Ops, Finance Ops | CRM Admin |  |
| 2.2 |  | Review SQL outputs and approve candidates for UAT | Data Steward | CRM Product Owner | Sales Ops, Finance Ops | CRM Admin |  |
| Phase 3 – Execution in UAT | Validate merge behavior safely | Execute approved deduplication candidates in UAT | CRM Admin | CRM Product Owner | Data Steward | Sales Ops, Finance Ops | W5 |
| 3.1 |  | Validate record reassignment behavior (Accounts, Opportunities, Activities, Contacts) | Data Steward | CRM Product Owner | Sales Ops, Finance Ops | CRM Admin |  |
| 3.2 |  | Validate financial, reporting, and integration outcomes | IT / Integration Lead | CRM Product Owner | Finance Ops | CRM Admin |  |
| 3.3 |  | Approve UAT results and authorize Production execution | CRM Product Owner | Exec Sponsor | Data Steward, IT, Finance Ops | CRM Admin |  |
| Phase 4 – Execution in Production | Perform controlled Production deduplication | Re-run SQL preview to confirm no material changes since UAT | Data Steward | CRM Product Owner | CRM Admin | Sales Ops | W6 |
| 4.1 |  | Execute approved merges in Production (controlled batches) | CRM Admin | CRM Product Owner | Data Steward | Exec Sponsor |  |
| 4.2 |  | Validate post-merge record reassignment (ownership, territory, sales credit) | Data Steward | CRM Product Owner | Sales Ops, Finance Ops | Exec Sponsor |  |
| 4.3 |  | Validate downstream integrations (ERP, BI, Finance) | IT / Integration Lead | CRM Product Owner | Finance Ops | CRM Admin |  |
| Phase 5 – Stabilization & BAU Controls | Confirm outcomes and prevent recurrence | Complete post-merge validation and close execution | CRM Admin | CRM Product Owner | Data Steward | Exec Sponsor | W6- W7 |
| 5.1 |  | Enhance account-creation controls to prevent duplicates | CRM Admin | CRM Product Owner | Data Steward | CRM Users |  |
| 5.2 |  | Conduct quarterly data quality and duplicate reviews | Data Steward | CRM Product Owner | Sales Ops, Finance Ops | Exec Sponsor |  |

## 5. Record Reassignment Control

When Accounts are merged in Dynamics 365, all related records (e.g. Contacts, Opportunities, Activities, Orders) are reassigned to the surviving Account.
Record reassignment is considered a material business event and must be explicitly validated:

- Before UAT execution

- Before Production Execution

- Immediately after Production execution

Any incorrect reassignment must trigger execution pause and assessment.

## 6. Production Rollback Framework (Environment Restore)

### Rollback Model

Production rollback for deduplication is performed by restoring the entire Dynamics 365 environment to the last approved pre-execution backup. Partial or record-level rollback is not supported.

This action overwrites all changes made since the backup.

### 6.1 Rollback Triggers

Rollback must be initiated if any of the following occur:

Data Integrity Triggers

- Incorrect merges across Account Types or Purposes

- Widespread incorrect ownership or territory reassignment

- Structural corruption of Account hierarchies

Financial Triggers

- Incorrect reassignment of Orders, Invoices, or Open Revenue

- Incorrect application of credit limits or payment terms

- Unreconcilable discrepancies with downstream financial systems

Reporting Triggers

- Material sales credit misallocation

- Incorrect territory or pipeline reporting

- Loss of historical audit traceability

Technical Triggers

- Integration failures attributable to merges

- Platform instability or automation failures

- Inability to validate outcomes within acceptable timeframes

### 6.2 Production Rollback Procedure

- Pause Execution
Immediately halt all Production deduplication activity.

- Assess Impact
Confirm scope of impact and identify restore point.

- Approve Restore
Executive approval to restore environment and acknowledge data loss since backup.

- Execute Restore
Restore Production environment using Dynamics 365 platform backup.

- Post-Restore Validation
Validate Accounts, ownership, territories, financials, integrations, and reporting.

- Resume or Terminate Programmed
Resume with corrected logic or terminate pending redesign.

### 6.3 Rollback RACI Summary

| Phase | Rollback Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- | --- |
|  | Halt Production execution | CRM Admin | CRM Product Owner | — | Exec Sponsor |
|  | Assess impact & confirm restore requirement | Data Steward | CRM Product Owner | Sales Ops, Finance Ops, IT | Exec Sponsor |
|  | Approve environment restore | CRM Product Owner | Exec Sponsor | IT, Finance Ops | CRM Admin |
|  | Execute D365 environment restore | IT / Platform Admin | CRM Product Owner | CRM Admin | Exec Sponsor |
|  | Validate post-restore environment | CRM Admin | CRM Product Owner | Data Steward, Sales Ops, Finance Ops | Exec Sponsor |
|  | Resume or terminate deduplication | — | Exec Sponsor | CRM Product Owner | Stakehold |

## 7. Final Governance Statement

This execution and rollback model ensures that Account deduplication in Dynamics 365 is:

- Controlled

- Auditable

- Risk-managed

- Repeatable

- Aligned to enterprise change standards

## 8. Execution Timeline

The deduplication project is planned over approximately 6–8 weeks. Each phase is gated by validation and formal approval before progression.

Governance & Readiness: Week 1

SQL Previews & Validation: Weeks 2–3

UAT Execution & Validation: Week 4

Production Execution: Week 5

Stabilization & BAU Controls: Weeks 6–7

### (Gantt Chart)